Timetable for data collection changes 2027-28

Health Services Data managed data collections; VAED, VEMD, ESIS, VINAH, VCDC and AIMS-hosted collections

OFFICIAL

| Key Dates | Description |
| --- | --- |
| Monday 20 July 2026 | Call for proposals Email sent to HDSS Bulletin list |
| Friday 31 July 2026 5.00pm | Deadline for submission of proposals |
| Tuesday 15 September 2026 | First Annual Changes Governance Committee meeting Review proposals before release for consultation |
| Tuesday 6 Oct 2026 | Proposals documents published on HDSS website for feedback Email sent to HDSS Bulletin list with the feedback proforma links |
| Tuesday 20 Oct 2026 5.00pm | Deadline for comment on proposals documents |
| Thursday 19 Nov 2026 | Second Annual Changes Governance Committee meeting Decision on whether to recommend accepting or rejecting each proposal |
| Friday 11 Dec 2026 | Recommendations to the Data Steward, Hospitals Victoria Seeking approval by Friday 11 December 2026 |
| Thursday 31 Dec 2026 | Final specifications for revisions to data collections Email sent to HDSS Bulletin list |
| Mid Jan 2027 | Final specifications for revisions to data collections published Published on HDSS website |
| Wednesday 30 June 2027 | Release data collection manuals Published on HDSS website |
| Thursday 1 July 2027 | New data collection specifications implemented |

To receive this document in another format, email the HDSS helpdesk <hdss.helpdesk@health.vic.gov.au> Authorised and published by the Victorian Government, 1 Treasury Place, Melbourne. © State of Victoria, Australia, Department of Health, July 2026. Available at HDSS annual changes <https://www.health.vic.gov.au/data-reporting/health-data-standards-and-systems>